## Timeline
| MILESTONE 1+2 | MILESTONE 3 | MILESTONE 4 | MILESTONE 5 | MILESTONE 6 | MILESTONE 7
| INITIATION | ANALYSIS | DESIGN | CODING | TESTING | CLOSING
CW 37
CW 38
CW 39 | « 29/09/2021
CW 40
CW 41
CW 42
CW 43 | « 27/10/2021
CW 44 |  | « 05/11/2021
CW 45
CW 46 |  |  | « 19/11/2021
CW 47
CW 48 |  |  |  | « 03/12/2021
CW 49
CW 50 |  |  |  |  | « 15/12/2021 | « 17/12/2021
| Group Formation & | Use Case Description | Sequence Diagram | Code | Unit Testing | Report writing
Topic Selection
|  | Actor Description | Design Class Diagram | Wireframe | System Testing | final Project Report
| Group Contract |  |  |  |  | final Process Report
|  | Test Cases | ER Diagram (global) | Application prototype | Integration Testing
| Kick Off |  |  | (MVP)
|  | Use Case Diagram | Application blueprint |  | Acceptance Testing
final
| Project Description | Domain Model |  |  | Test report
|  | (finish analysis phase) |  |  | (finish testing phase)
approval
Project Description

## Timeline - IDX
| MILESTONE 1+2 | MILESTONE 3 | MILESTONE 4 | MILESTONE 5 | MILESTONE 6 | MILESTONE 7
| INITIATION | ANALYSIS | DESIGN | CODING | TESTING | CLOSING
CW 37
CW 38
CW 39 | « 29/09/2021
CW 40
CW 41
CW 42
CW 43 | « 27/10/2021
CW 44 |  | « 05/11/2021
CW 45
CW 46 |  |  | « 19/11/2021
CW 47
CW 48 |  |  |  | « 03/12/2021
CW 49
CW 50 |  |  |  |  | « 15/12/2021 | « 17/12/2021
| Group Formation & | Use Case Description | Sequence Diagram | Code | Unit Testing | Report writing
Topic Selection
|  | Actor Description | Design Class Diagram | Wireframe | System Testing | final Project Report
| Group Contract |  |  |  |  | final Process Report
|  | Test Cases | ER Diagram (global) | Application prototype | Integration Testing
| Kick Off |  |  | (MVP)
|  | Use Case Diagram | Application blueprint |  | Acceptance Testing
final
| Project Description | Domain Model |  |  | Test report
|  | (finish analysis phase) |  |  | (finish testing phase)
approval
Project Description